GRUBER

Procurement & Inventory Transformation

30-Day Baseline Assessment and Launch Plan

Mission Transform purchasing from a decentralized administrative activity into a shared strategic capability that improves supplier performance, inventory availability, working capital, operational efficiency, quality, and profitability across all five businesses.

Prepared as an execution-ready starting package

# 1. Executive Mandate

The organization should launch one enterprise procurement program while preserving the operating needs of each business. Centralization should begin with visibility, common data, supplier leverage, and governance—not by immediately removing all local purchasing authority.

Develop and mentor the purchasing and inventory teams.

Build strategic supplier partnerships and negotiate stronger pricing, contracts, service levels, and payment terms.

Improve inventory accuracy, availability, turns, and working-capital performance.

Identify waste, duplicate activity, fragmented suppliers, unnecessary freight, and weak processes.

Create shared systems that support Sales, Operations, Manufacturing, Accounting, Service, Projects, and Leadership.

Use purchasing and inventory data to improve decisions and validate measurable financial results.

Operating principle Centralize standards, data, contracts, reporting, and supplier strategy. Keep appropriate operational purchasing close to the teams that understand customer, production, project, service, and vehicle requirements.

## Business Scope

| Business | Primary Purchasing Profile | Initial Reporting Emphasis |
| --- | --- | --- |
| Gruber Communications | Raw materials, cable, connectors, fabricated metal, finished goods and e-commerce inventory | Material yield, stock availability, BOM accuracy, supplier pricing and finished-goods turns |
| Gruber Power Services | UPS equipment, batteries, service parts, refurbished equipment and field inventory | High-value inventory, legacy parts, service availability, repair-versus-replace and supplier performance |
| Gruber Technical Services | Project materials, electrical products, structured cabling, flooring and subcontracted services | Job commitments, delivery risk, material variance, returns, change orders and project margin |
| Gruber Motor Company | Tesla parts, battery modules, donor components, repair materials and restoration supplies | Legacy inventory, donor-part recovery, work-order material usage and restoration profitability |
| EV Preserve | Facility, charging, monitoring, security, transportation and vehicle-care supplies | Occupancy support, customer profitability, service referrals and facility operating efficiency |

# 2. First 30 Days

| Timing | Primary Work | Deliverables | Leadership Decision |
| --- | --- | --- | --- |
| Days 1-5 | Confirm governance, interview each function, map current purchasing and inventory processes, identify systems and data owners. | Transformation team; discovery tracker; current-state maps; data-source register. | Confirm sponsor, program lead, company representatives, scope, and access. |
| Days 6-12 | Collect 12-24 months of purchasing history, current inventory, supplier records, item records, contracts, freight, returns and warranty data. | Raw baseline files; data-quality issue list; supplier and item normalization rules. | Approve common company, supplier, category, item, location, and purpose standards. |
| Days 13-20 | Load and validate data, reconcile totals with Accounting, build initial spend, inventory-aging and open-PO views. | Validated baseline; top suppliers; category spend; inventory exposure; delivery risks. | Select initial pilot category and immediate containment actions. |
| Days 21-30 | Build savings pipeline, prepare supplier negotiations, approve interim policies, define 90-day rollout. | Executive scorecard; opportunity register; pilot charter; policy; 90-day roadmap. | Authorize negotiations, pilot execution, targets, and recurring leadership reviews. |

## Immediate Deliverables

One consolidated supplier master with duplicate supplier records identified.

One common purchasing-category structure across all five companies.

A validated purchasing-spend baseline.

A current inventory-value and aging baseline.

An open and past-due purchase-order report.

A ranked list of the first ten savings, service, cash, or risk opportunities.

A Gruber Power pilot charter for one high-value category.

An interim procurement and inventory policy.

# 3. Governance and Accountability

| Role | Primary Responsibility | First 30 Days | Ongoing Cadence | Decision Rights |
| --- | --- | --- | --- | --- |
| Executive Sponsor | Remove barriers and align company leadership. | Approve scope, team, access and targets. | Monthly steering review. | Policy, investment, cross-company escalation. |
| Procurement Transformation Lead | Own program delivery, supplier strategy and reporting. | Run discovery, data collection, baseline and pilot. | Weekly operations; monthly executive reporting. | Process standards, negotiation strategy, recommended awards. |
| Company Representatives | Represent operational needs and validate data. | Complete interviews, identify exceptions and confirm priorities. | Weekly company review. | Local requirements and execution within approved standards. |
| Accounting | Validate financial baselines, costs and savings. | Reconcile purchasing and inventory totals. | Monthly validation. | Savings validation, costing and financial controls. |
| Inventory/Warehouse Leads | Own receiving, locations, counts, transfers and adjustments. | Document current controls and data quality. | Daily exceptions; weekly accuracy review. | Inventory transactions within policy. |
| IT/Data | Support extracts, field mapping and system controls. | Provide data and system documentation. | As required by roadmap. | Technical implementation and access controls. |

## Recommended Meeting Cadence

Daily during data collection: 15-minute issue resolution among the transformation lead, Accounting, and data owners.

Weekly: 45-minute cross-company purchasing and inventory working session.

Biweekly during launch: supplier, inventory, and savings opportunity review.

Monthly: executive scorecard and decisions on risk, cash, savings, and policy.

Quarterly: strategic supplier business reviews and category planning.

# 4. Standardized Discovery Interview Guide

Use the same questions with each business and function. Record answers in the Discovery Tracker sheet so differences and common problems can be compared.

## Demand and requests

What triggers a purchase request?

Who determines quantity, specification, supplier, and required date?

How are customer, production, service, project, and facility demands distinguished?

Which purchases are predictable, and which are typically urgent?

## Approval and ordering

Who can approve purchases, at what dollar thresholds, and in which systems?

Are purchase orders always issued before an order is placed?

How are emergency, credit-card, online, and verbal purchases controlled?

How are supplier acknowledgements and delivery dates captured?

## Receiving and inventory

Who receives products and verifies quantity, condition, serial number, and documentation?

Where can inventory be stored: warehouse, production, project site, service vehicle, repair bench, donor stock, or another business?

How are transfers, consumption, scrap, returns, cores, donor parts, and adjustments recorded?

How often are cycle counts performed, and what causes discrepancies?

## Suppliers and contracts

Which suppliers are strategic, sole-source, high-risk, or difficult to replace?

Where are contracts, pricing, rebates, warranty terms, lead times, and freight agreements stored?

Are different Gruber companies buying the same products from different suppliers or at different prices?

How are supplier quality, delivery, invoice accuracy, and responsiveness measured?

## Financial and operational impact

How are purchases tied to inventory, customer orders, manufacturing orders, service work orders, projects, vehicle repairs, or operating expenses?

Where do stockouts, emergency freight, slow-moving inventory, rework, and warranty failures create the most cost?

Which reports are trusted today, and which decisions are being made without reliable data?

What is the most valuable improvement that could be achieved within 90 days?

# 5. Initial Data Request

Request data for the most recent 12-24 months where available, plus the current inventory position.

| Dataset | Required Fields | Primary Owner | Purpose |
| --- | --- | --- | --- |
| Purchase orders and receipts | PO, dates, company, location, buyer, supplier, item, description, category, quantity, cost, freight, status, project/work order | Purchasing / Accounting | Spend, open commitments, price variance, delivery risk |
| Supplier invoices and credits | Supplier, invoice, PO, dates, line costs, freight, tax, credit, payment terms | Accounting | Reconcile spend, invoice accuracy, true landed cost |
| Current inventory | Location, item, description, quantity, cost, last use, serial/lot, status | Inventory / Accounting | Value, aging, availability, transfers and accuracy |
| Item master | SKU, description, category, UOM, manufacturer, part number, supplier, lead time, min/max, standard and last cost | Inventory / Operations | Normalize items and planning controls |
| Supplier master and contracts | Legal name, contacts, categories, terms, agreements, dates, pricing, warranty, risk | Purchasing / Legal / Accounting | Consolidation, negotiation and compliance |
| Sales and material usage | Orders, shipments, COGS, work-order issues, manufacturing consumption | Sales / Operations / Manufacturing | Demand, turns, forecast and service levels |
| Projects and work orders | Budget, purchased, issued, returned, scrap, labor, customer, margin | Projects / Service / Accounting | Material variance and profitability |
| Returns, warranty and quality | Supplier, item, failure, quantity, cost, disposition, recovery | Quality / Service / Accounting | True supplier cost and recovery |

## Minimum Data Standards

Every transaction must identify the company and location.

Every supplier should use one normalized supplier ID and name.

Every item should use a consistent item ID, description, category, and unit of measure.

Every purchase should identify its business purpose and, when applicable, a customer order, manufacturing order, service work order, project, or vehicle repair/restoration.

Every inventory movement should use a documented transaction and reason code.

# 6. Initial Reporting Package

| Report | Key Question | Primary Users | Cadence |
| --- | --- | --- | --- |
| Executive scorecard | Are purchasing, inventory, suppliers, cash and savings improving? | Leadership | Monthly |
| Consolidated spend | What are we buying, from whom, and at what total cost? | Leadership / Purchasing / Accounting | Monthly |
| Open and past-due POs | Which commitments or late deliveries threaten customers and operations? | Purchasing / Operations | Daily or weekly |
| Inventory value and aging | Where is cash tied up, and which inventory requires action? | Leadership / Inventory / Accounting | Monthly |
| Supplier scorecard | Which suppliers deserve growth, correction, or replacement? | Purchasing / Operations / Quality | Monthly or quarterly |
| Stockout and expedite | Where are shortages creating delay, lost revenue or rush cost? | Operations / Purchasing / Sales | Weekly |
| Project/work-order material variance | Are jobs and repairs consuming materials as planned? | Projects / Service / Accounting | Weekly or monthly |
| Savings pipeline | Which opportunities are identified, approved, implemented and financially validated? | Leadership / Purchasing / Accounting | Monthly |

The accompanying Gruber Procurement Baseline Workbook contains the initial data structures, formulas, KPI definitions, scorecards, discovery tracker, 30-day project plan, supplier master, item master, purchase-order input, inventory snapshot, supplier scorecard, and savings pipeline.

# 7. Recommended Pilot: Gruber Power Services

Begin with one high-value, repeat-purchase category at Gruber Power Services. Batteries, UPS service parts, or refurbished-equipment components are strong candidates because they combine working-capital exposure, emergency availability, legacy support, supplier leverage, and measurable service impact.

| Pilot Element | Requirement |
| --- | --- |
| Category scope | One defined category with meaningful annual spend and operational importance. |
| Baseline | 12-24 months of spend, unit pricing, freight, lead time, stockouts, returns, inventory and demand. |
| Supplier analysis | Current suppliers, pricing, terms, delivery, quality, risk and alternative sources. |
| Inventory analysis | Locations, min/max levels, service criticality, aging, legacy requirements and transferable stock. |
| Negotiation | Consolidated demand, target price, terms, freight, lead time, service levels, warranty and stocking support. |
| Measures | Savings, availability, expedite reduction, turns, inventory value, supplier delivery and quality. |
| Duration | Initial 60-90 day implementation after the baseline month. |

Pilot success standard The pilot must improve financial performance without reducing service readiness. Savings should be validated by Accounting and adjusted for volume, specification, commodity and service-level changes.

# 8. Interim Procurement and Inventory Policy

Use approved suppliers unless an emergency or documented exception is authorized.

Issue a purchase order before placing an order whenever the system and circumstances allow.

Apply documented approval thresholds by company, department, and purchase type.

Use emergency-buy and expedite reason codes; review repeated exceptions weekly.

Search available inventory across Gruber locations and businesses before buying duplicate stock.

Reference the applicable customer order, manufacturing order, service work order, project, vehicle repair/restoration, facility expense, or capital request.

Require supplier onboarding, tax, banking, insurance, quality, cybersecurity, and conflict checks appropriate to the relationship.

Store current contracts, pricing, payment terms, freight terms, warranties, and service levels centrally.

Record all receipts, transfers, issues, returns, cores, donor-part harvests, scrap, write-offs, and adjustments.

Do not classify rare legacy service parts as obsolete without technical and service review.

Validate reported savings through Accounting before presenting them as realized financial results.

# 9. First Opportunity Tests

| Test | Analysis | Possible Action |
| --- | --- | --- |
| Duplicate suppliers | Compare normalized supplier names and category overlap across businesses. | Consolidate demand and negotiate enterprise pricing. |
| Price differences | Compare identical items, specifications and landed cost by supplier and business. | Standardize preferred source and contract price. |
| Inventory transfers | Find required items available in another location or business. | Transfer before purchasing new stock. |
| Old inventory | Separate excess/obsolete stock from strategic legacy inventory. | Return, sell, bundle, refurbish, harvest, recycle or retain intentionally. |
| Emergency freight | Identify repeated expedite reasons, suppliers, items and teams. | Correct planning, stocking, approvals or supplier lead-time performance. |
| Open PO risk | Rank late or unconfirmed orders by customer, project and service impact. | Escalate supplier, expedite strategically or source alternatives. |
| Warranty leakage | Compare supplier failures and customer/service costs with credits recovered. | Strengthen claims, terms and supplier corrective action. |
| Project leftovers | Compare project purchases, issues, returns, scrap and remaining materials. | Return to stock, supplier or future project; improve estimating. |

# 10. Measures of Success

| Area | Baseline Measure | Expected Direction |
| --- | --- | --- |
| Purchasing | Total spend, price variance, off-contract spend and supplier count | Lower avoidable cost and fragmentation |
| Inventory | Value, turns, days on hand, accuracy, aging and stockouts | Higher accuracy and availability; lower unnecessary investment |
| Suppliers | On-time delivery, completeness, quality, invoice accuracy and risk | Higher service and accountability |
| Operations | Past-due POs, expedites, material delays and repeated emergencies | Fewer disruptions and faster resolution |
| Cash | Open commitments, advance payments, excess inventory and payment terms | Improved working capital |
| Profitability | Material variance, warranty leakage, freight and realized savings | Higher validated margin contribution |
| Team | Process ownership, report usage, training and corrective-action closure | Stronger capability and consistent execution |

## Leadership Decisions Required Now

Name the executive sponsor and procurement transformation lead.

Assign one accountable representative from each of the five companies.

Authorize access to purchasing, inventory, accounting, sales, manufacturing, project, service and work-order data.

Approve the common data standards and the use of the baseline workbook.

Authorize Gruber Power Services as the initial pilot and select its first category.

Set the date for the first executive baseline review at the end of the 30-day period.

Next action Distribute the workbook and this launch plan to the assigned team. Hold a 60-minute kickoff, begin discovery interviews immediately, and require each data owner to confirm availability and delivery dates for the requested files.