## Read Me
Gruber Procurement & Inventory Baseline Workbook
Purpose
Use this workbook to establish a centralized purchasing and inventory baseline across all five Gruber businesses. Enter or import supplier, item, purchase-order, inventory, and savings data into the yellow-header input sheets. The Executive Dashboard and analysis sheets update from those records.
Recommended sequence | Action
1 | Complete the Company Discovery Tracker with leaders from each business.
2 | Load the Supplier Master and normalize duplicate supplier names.
3 | Load the Item Master and assign common purchasing categories.
4 | Import 12-24 months of purchase-order history.
5 | Import the current inventory snapshot by location.
6 | Review dashboard exceptions and populate the Savings Pipeline.
Input convention
Yellow headers identify fields intended for entry or import. Use one consistent supplier name, item ID, unit of measure, company code, location, and category. Every purchase should be tied to a business purpose: inventory replenishment, customer order, manufacturing order, service work order, construction project, vehicle repair/restoration, facility expense, or capital investment.

## Companies
Company Scope
Code | Business | Operating Scope | Website
GC | Gruber Communications | Manufacturing, distribution, custom cabling and network infrastructure | https://grubercommunications.com/
GPS | Gruber Power Services | Critical power equipment, service, repair, maintenance and asset recovery | https://gruberpower.com/
GTS | Gruber Technical Services | Electrical, structured cabling, data-center construction and raised flooring | https://grubertechnical.com/
GMC | Gruber Motor Company | Tesla and EV repair, engineering, restoration, parts and vehicle support | https://grubermotors.com/
EVP | EV Preserve | Managed storage, monitoring and preservation for collectible electric vehicles | https://evpreserve.com/

## Discovery Tracker
Company Discovery & Process Assessment
Company Code | Function | Process Owner | Current System | Current Process Summary | Primary Pain Point | Data Available? | Risk | Priority | Next Action
GC | Purchasing
GC | Inventory/Warehouse
GC | Sales
GC | Operations
GC | Manufacturing
GC | Accounting
GC | Service
GC | Project Management
GC | Leadership
GC | IT/Data
GPS | Purchasing
GPS | Inventory/Warehouse
GPS | Sales
GPS | Operations
GPS | Manufacturing
GPS | Accounting
GPS | Service
GPS | Project Management
GPS | Leadership
GPS | IT/Data
GTS | Purchasing
GTS | Inventory/Warehouse
GTS | Sales
GTS | Operations
GTS | Manufacturing
GTS | Accounting
GTS | Service
GTS | Project Management
GTS | Leadership
GTS | IT/Data
GMC | Purchasing
GMC | Inventory/Warehouse
GMC | Sales
GMC | Operations
GMC | Manufacturing
GMC | Accounting
GMC | Service
GMC | Project Management
GMC | Leadership
GMC | IT/Data
EVP | Purchasing
EVP | Inventory/Warehouse
EVP | Sales
EVP | Operations
EVP | Manufacturing
EVP | Accounting
EVP | Service
EVP | Project Management
EVP | Leadership
EVP | IT/Data

## Supplier Master
Centralized Supplier Master
Supplier ID | Normalized Supplier Name | Legal Name | Primary Category | Companies Served | Contact Name | Email | Phone | Payment Terms | Contract Start | Contract End | Preferred? | Risk Rating | Annual Spend | On-Time Delivery % | Quality Acceptance % | Notes

## Item Master
Centralized Item / SKU Master
Item ID | Company Code | SKU | Normalized Description | Category | Subcategory | Manufacturer | Manufacturer Part # | Unit of Measure | Primary Supplier ID | Standard Cost | Last Cost | Lead Time Days | Min Qty | Max Qty | Reorder Point | Strategic Legacy? | Active?

## Purchase Orders
Purchase Order History & Open Commitments
PO Number | PO Date | Company Code | Location | Department | Buyer | Supplier ID | Supplier Name | Item ID | Description | Category | Quantity | Unit Cost | Line Total | Required Date | Expected Date | Received Date | Status | Business Purpose | Project / Work Order | Expedite Freight

## Inventory Snapshot
Current Inventory Snapshot
Snapshot Date | Company Code | Location | Item ID | SKU | Description | Category | Quantity On Hand | Unit Cost | Inventory Value | Last Usage Date | Age Days | Age Classification | Strategic Legacy? | Minimum Qty | Maximum Qty | Recommended Action

## Savings Pipeline
Savings & Improvement Pipeline
Opportunity ID | Company / Enterprise | Category | Opportunity Description | Current Annual Cost | Expected Annual Savings | Implementation Cost | Net First-Year Benefit | Owner | Status | Target Date | Realized Savings | Accounting Validated? | Risk | Next Step | Notes

## Supplier Scorecard
Supplier Performance Scorecard
Supplier ID | Supplier Name | Annual Spend | On-Time Delivery % | Complete Delivery % | Quality Acceptance % | Invoice Accuracy % | Responsiveness Score | Contract Compliance % | Risk Score | Weighted Score | Grade | Review Owner | Improvement Action

## KPI Definitions
Procurement & Inventory KPI Dictionary
KPI | Definition | Formula / Method | Owner | Cadence
Total Purchasing Spend | Total purchase-order line value for the period. | Sum of PO line totals | Purchasing | Monthly
Open PO Value | Value committed but not fully received or canceled. | Open + partially received + past-due PO line values | Purchasing | Weekly
Purchase Price Variance | Difference between actual purchase price and standard or contract price. | (Actual Price - Baseline Price) × Quantity | Purchasing/Accounting | Monthly
Inventory Value | Quantity on hand multiplied by unit cost. | Qty On Hand × Unit Cost | Inventory/Accounting | Monthly
Inventory Turns | How many times inventory is consumed or sold annually. | Annual COGS ÷ Average Inventory | Accounting/Operations | Monthly
Days Inventory on Hand | Estimated days represented by current inventory. | 365 ÷ Inventory Turns | Accounting/Operations | Monthly
Inventory Accuracy | Agreement between system and physical quantities. | Correct count lines ÷ Total count lines | Warehouse | Cycle count
Supplier On-Time Delivery | Supplier lines received by confirmed required date. | On-time receipts ÷ Total receipts | Purchasing | Monthly
Supplier Quality Acceptance | Supplier lines accepted without defect or return. | Accepted lines ÷ Received lines | Quality/Operations | Monthly
Stockout Rate | Demand lines that could not be filled when required. | Stockout demand lines ÷ Total demand lines | Operations | Weekly
Expedite Cost | Rush freight and emergency-buying cost. | Sum of expedite freight and rush fees | Purchasing | Monthly
Excess & Obsolete Value | Inventory classified as excess or obsolete, excluding approved strategic legacy stock. | Sum inventory value by aging classification | Leadership/Accounting | Monthly
Realized Savings | Savings confirmed after implementation and validated by Accounting. | Baseline cost - actual cost, adjusted for volume/spec changes | Purchasing/Accounting | Monthly

## 30-Day Plan
30-Day Procurement Transformation Launch Plan
Week | Workstream | Action | Owner | Business Scope | Deliverable | Status | Due Date
Week 1 | Governance | Name executive sponsor, program lead, and one representative from each business. |  | All five | Confirmed transformation team | Not Started | 2026-07-27
Week 1 | Discovery | Complete the standardized purchasing and inventory process interviews. |  | All five | Current-state process maps | Not Started | 2026-07-31
Week 1 | Data | Identify all systems and owners for supplier, item, PO, invoice, inventory, sales, project, and work-order data. |  | All five | Data-source register | Not Started | 2026-07-31
Week 2 | Data | Export 12-24 months of purchasing history and the current inventory snapshot. |  | All five | Baseline data files | Not Started | 2026-08-05
Week 2 | Master Data | Normalize supplier names and assign common category and company codes. |  | All five | Consolidated supplier master | Not Started | 2026-08-07
Week 2 | Master Data | Normalize item descriptions, units of measure, and primary suppliers. |  | All five | Initial item master | Not Started | 2026-08-07
Week 3 | Reporting | Load data into the baseline workbook and validate totals with Accounting. |  | All five | Validated spend and inventory baseline | Not Started | 2026-08-12
Week 3 | Analysis | Identify duplicate suppliers, price differences, old inventory, stockouts, expedites, and open-PO risks. |  | All five | Top opportunity register | Not Started | 2026-08-14
Week 3 | Pilot | Select one Gruber Power category for the first procurement pilot. |  | Gruber Power | Pilot charter | Not Started | 2026-08-14
Week 4 | Supplier Strategy | Prepare negotiation plans for the highest-value supplier and category opportunities. |  | Enterprise | Supplier negotiation briefs | Not Started | 2026-08-19
Week 4 | Governance | Approve purchasing thresholds, supplier onboarding, PO, emergency-buy, and inventory-transfer rules. |  | All five | Interim procurement policy | Not Started | 2026-08-21
Week 4 | Leadership | Present baseline, risks, savings pipeline, pilot scope, and 90-day roadmap. |  | All five | Executive review package | Not Started | 2026-08-25

## Executive Dashboard
Executive Procurement & Inventory Scorecard
KPI | Current Baseline | Company | Purchasing Spend | Inventory Value
Total Purchasing Spend | 0 | Gruber Communications | 0 | 0
Open / Past-Due PO Value | 0 | Gruber Power Services | 0 | 0
Inventory Value | 0 | Gruber Technical Services | 0 | 0
Excess + Obsolete Inventory | 0 | Gruber Motor Company | 0 | 0
Strategic Legacy Inventory | 0 | EV Preserve | 0 | 0
Expedite Freight | 0
Expected Annual Savings | 0
Leadership Interpretation
Start with data completeness and comparability. Once the five companies use normalized supplier, item, category, company, location, and business-purpose fields, leadership can consolidate demand, negotiate enterprise agreements, transfer usable inventory between businesses, control emergency buying, and validate savings with Accounting.